| # | Activity | Predecessor | Work Products / Outcomes | Who / Resources | When | Effort Hours |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Review & Refine Project Definition | None | Updated Project Definition (living document), clarified scope & assumptions | Calvin Cunningham | Week 1 | 4 |
| 2 | Identify Business Rules & Requirements | 1 | Documented business rules (vendor approval workflow, booth availability rules, permit logic, operational periods) | Calvin | Week 1 | 5 |
| 3 | Build Conceptual ERD (Business Object Model) | 2 | Conceptual ER Diagram identifying entities & relationships | Calvin, Visio | Week 2 | 6 |
| 4 | Develop Data Flow Diagram (Context + Level 1) | 3 | DFD showing system interactions and data movement | Calvin | Week 2 | 5 |
| 5 | Create State Transition Diagram (Vendor Application) | 3 | State diagram documenting lifecycle from Draft → Submitted → Approved → Assigned → Active → Completed | Calvin | Week 2 | 4 |
| 6 | Convert to Logical Data Model | 3 | Logical ERD with PKs, FKs, attributes, cardinality | Calvin, SQL Server tools | Week 3 | 6 |
| 7 | Develop Physical Database Design | 6 | SQL DDL scripts (CREATE TABLE, constraints, indexes) | Calvin, SQL Server | Week 3 | 6 |
| 8 | Insert Sample Data & Build Queries | 7 | Sample dataset + operational queries (vendor list, booth utilization, participation report) | Calvin | Week 4 | 5 |
| 9 | Validate, Test & Refine | 8 | Adjusted models, tested edge cases (reassignment, rejected applications, booth holds) | Calvin | Week 4 | 4 |
| 10 | Final Documentation & Submission | 9 | Final artifact package (Project Definition + 4 diagrams) for Canvas submission | Calvin | Week 4 | 3 |