## Sheet1
# | Activity | Predecessor | Work Products / Outcomes | Who / Resources | When | Effort Hours
1 | Review and refine project definition | None | Updated project definition, clarified scope, assumptions, and boundaries | Calvin; Word, class notes, Canvas | Week 1 | 4
2 | Identify business rules and naming conventions | 1 | Business rules list, naming standards for tables, keys, and diagrams | Calvin; class materials, instructor feedback | Week 2 | 5
3 | Build conceptual ERD / business object model | 2 | Conceptual data model showing entities and high-level relationships | Calvin; Visio / draw.io | Week 3 | 6
4 | Create conceptual architecture drawing | 2 | High-level architecture diagram supporting business and technical discussion | Calvin; Visio | Week 4 | 4
5 | Develop logical data model | 3 | Logical model with PKs, FKs, and cardinalities | Calvin; Visio, logical modeling notes | Week 5 | 6
6 | Review collaboration points with team | 3,4,5 | Notes on shared entities, dependencies, and alignment with team work | Calvin + class team; open lab sessions | Week 6 | 3
7 | Design physical data model | 5 | Physical table structure and relationship layout for SQL Server | Calvin; Visio / SSMS diagram tools | Week 7 | 5
8 | Build reference and base tables in SQL Server | 7 | Working SQL script for lookup tables and core entities | Calvin; SSMS | Week 8 | 6
9 | Build associative and transaction tables | 8 | Working SQL script for join and transaction tables | Calvin; SSMS | Week 9 | 6
10 | Add audit columns and history design | 8,9 | Audit field standards and selected history table plan | Calvin; SQL Server, history example | Week 10 | 4
11 | Implement history tables and triggers | 10 | At least four history tables and functional update/delete triggers | Calvin; SQL Server | Week 11 | 6
12 | Insert sample data and test workflows | 8,9,11 | Test records for vendors, applications, booths, and participation | Calvin; SQL Server queries | Week 12 | 5
13 | Validate business rules and constraints | 12 | Constraint checks, relationship validation, cleanup notes | Calvin; SQL Server, instructor feedback | Week 13 | 4
14 | Organize GitHub repository and project artifacts | 6,12 | GitHub repo structure, committed scripts and documentation | Calvin; GitHub, Git Bash | Week 14 | 4
15 | Finalize documentation and visuals | 13,14 | Polished diagrams, updated plan, updated definition, progress summary | Calvin; Word, Visio, Canvas files | Week 15 | 5
16 | Prepare class sharing and final submission | 15 | Final submission package and presentation-ready materials | Calvin | Week 16 | 3